## Milestones
To do area | Milestone | Owner
AWS setup | Script saving time per minute | Kristof
Data stream | List of data points | Ruben
Data stream | Fetch data elia API where possible | Kristof
Data stream | Scrape data required NRT | Kristof
Data stream | Data pre-processing script | Ruben
Optimization | Extracted forecasters | Ruben
Optimization | Optimization script | Ruben
Output visualization | web page linked to AWS setup script updating minutely | Ruben
Output visualization | Figure SoC/SI/imb price/decisions over time | Kristof/Ruben
Output visualization | Table current decisions | Kristof

## Timeline
|  | Week | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19
Area | Milestone
AWS setup | Script saving time per minute | bar: 2022-10-24 to 2022-11-07
Data stream | List of data points | bar: 2022-10-24
Data stream | Fetch data elia API where possible | bar: 2022-10-31
Data stream | Scrape data required NRT | bar: 2022-11-14 to 2022-11-28
Data stream | Data pre-processing script | bar: 2022-11-07; 2022-12-05 to 2022-12-12
Optimization | Extracted forecasters | bar: 2022-10-31 to 2022-11-07
Optimization | Optimization script | bar: 2022-11-28
Output visualization | web page linked to AWS setup script updating minutely | bar: 2022-11-14 to 2022-11-21
Output visualization | Figure SoC/SI/imb price/decisions over time | bar: 2022-11-28 to 2022-12-05
Output visualization | Table current decisions | bar: 2022-12-12